## Project Plan
2025-05-29
Deadline: | 2025-05-15 | Days Left: | -14 | Fully operational and deployed on: |  |  | 2025-05-22
Task | Sub task | Deliverable | Notes | Est. Days | Plan Start | Plan Act | Status
Define System Scope | Identify core functionalities | System requirements document | List of features & constraints | 3 | 2025-03-14 | 2025-03-16 | Complete
| Identify authorized users | User roles & permissions list | Define access control | 2 | 2025-03-17 | 2025-03-18 | Complete
Identify User Roles & Permissions | Define user roles (Admin, Instructor, Student) | Role list with access rights | Align with security requirements | 3 | 2025-03-19 | 2025-03-21 | Complete
| Implement Role-Based Access Control (RBAC) | Role access matrix | Security implementation | 4 | 2025-03-22 | 2025-03-25 | Complete
Design Database Schema | Create user tables | Database schema | Includes user & attendance tables | 4 | 2025-03-26 | 2025-03-29 | Complete
| Design attendance tracking tables | Attendance schema | Includes scanning records | 3 | 2025-03-30 | 2025-04-01 | Complete
Design API Endpoints | Develop User Management APIs | API endpoints for registration | Align with authentication system | 5 | 2025-04-02 | 2025-04-06 | Complete
| Develop Attendance APIs | API endpoints for tracking | Secure endpoints with RBAC | 5 | 2025-04-07 | 2025-04-11 | Complete
Develop Registration System | Implement student & instructor registration | Functional registration module | Includes ID photo upload | 6 | 2025-04-12 | 2025-04-17 | Complete
Implement User Authentication | Enable Multi-Factor Authentication (MFA) | Secure login system | Required for instructor logins | 5 | 2025-04-18 | 2025-04-22 | Complete
Implement Device Management | Register/unregister instructor devices | Device tracking system | Locate lost registered devices | 4 | 2025-04-23 | 2025-04-26 | Complete
Implement Barcode Scanning | Develop barcode scanner integration | Functional scanning system | Linked to attendance tracking | 6 | 2025-04-27 | 2025-05-02 | Complete
Develop Absence Drop Feature | Implement automatic absence drop logic | Auto-drop module | Tracks 3 consecutive absences | 4 | 2025-05-03 | 2025-05-06 | Complete
Generate Attendance Reports | Develop report generation system | Attendance reports (CSV/PDF) | Students can view records | 5 | 2025-05-07 | 2025-05-11 | Complete
Encrypt Sensitive Data | Apply data encryption methods | Secure database storage | Encryption for passwords & attendance | 3 | 2025-05-12 | 2025-05-14 | Complete
Initial System Testing | Perform preliminary evaluation | System assessment report | Identify major issues before testing | 1 | 2025-05-15 | 2025-05-15 | Complete
Apply Role-Based Access Control (RBAC) | Restrict unauthorized access | Secure access control system | Align with security policies | 3 | 2025-05-16 | 2025-05-18 | Complete
Finalizing System for Deployment | Fix bugs, optimize performance, finalize setup | Deployment-ready system | Ensure full functionality & security | 3 | 2025-05-19 | 2025-05-21 | Complete
Final System Deployment | Deploy on cloud-based storage | Fully deployed system | MongoDB Atlas or MySQL | 1 | 2025-05-22 | 2025-05-22 | Complete
Formulas:
Plan Start = IF([Plan Act, row above]<>"", [Plan Act, row above] + 1, "")

## Traceability Matrix
Traceability Matrix - Automated Attendance Tracking System
|  |  | UC1 | UC2 | UC3 | UC4 | UC5 | UC6 | UC7 | UC8 | UC9 | UC10 | UC11 | UC12 | UC13 | UC14
R01 | R01.01 | Authorized user must be able to upload student ID photos along with personal details (full name, student ID, year level, program, and faculty) during registration. | TRUE | TRUE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
| R01.02 | The system must allow authorized user to remove students or instructors from the system. | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE
| R01.03 | Authorized user must have the authority to unregister an instructor’s phone if necessary. | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE | FALSE | FALSE
| R01.04 | Only authorized users can access specific features. | TRUE | FALSE | FALSE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE
| R01.05 | Only authorized users can locate lost registered devices of the instructor. | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE
R02 | R02.01 | Instructors must be able to take attendance using ID Barcode scanning via registered devices (phones or laptops). | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE
| R02.02 | The system must allow instructors to drop students who have accumulated three consecutive absences. | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE
| R02.03 | The system must generate attendance report for authorized users. | FALSE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| R02.04 | Students must be able to view their attendance records per course. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE
R03 | R03.01 | Role-Based Access Control (RBAC) must be enforced to restrict access to sensitive data. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE
| R03.02 | Admin-controlled data encryption must be used to ensure data confidentiality. | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
| R03.03 | Multi-Factor Authentication (MFA) must be required for instructor logins. | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE
| R03.04 | The system must operate over HTTPS using SSL security protocols. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE
R04 | R04.01 | The system must use MongoDB Atlas or MySQL for cloud-based data storage. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
| R04.02 | The system must be accessible and scalable. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
| R04.03 | The system must not provide an API for integration with other university systems. | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | TRUE